## PRODUCT BACKLOG
PRODUCT BACKLOG
Task Group | User Story ID | Task Name | User Story | Estimate (size) | Priority | Sprint | Task owner | Estimated effort (HRs)
Authentication | DSM001 | Authentication | As a customer I need to be able to login to my account. | Small | 1 | 1 | Dustin | 4
| DSM002 | Sign up | As a customer I need to be able to sign up using different methodologies. | Small | 1 | 1 | Dustin | 2
| DSM003 | Reset Password | A a customer I need to be able to login to my account from any page on the website. | Small | 1 | 1 | Dustin | 4
Management | DSM004 | View list of applications | As a customer I need to be able to view all applications and details about each of them. | Medium | 1 | 2 | Dustin | 12
| DSM005 | Subscribe | As a customer I need to be able to subscribe to the application. | Medium | 1 | 2 | Dustin | 4
| DSM006 | Ubsubscribe | As a customer I need to be able to usubscribe to the application. | Medium | 1 | 2 | Dustin | 4
| DSM007 | View list of payment history | As a customer I need to be able to view all history payments and details about each of them. | Medium | 1 | 2 | Dustin | 6
| DSM008 | View list of benefits | As a customer I need to be able to view my benefits from using the application(s). | Medium | 1 | 2 | Dustin | 24
| DSM009 | View personal information | As a customer I need to be able to view and modify my personal information. | Medium | 1 | 2 | Dustin | 4
| DSM010 | Report/Feedback | As a customer I need to be able to report if the applications have any errors. | Medium | 1 | 2 | Dustin | 4
Analysis | DSM011 | Calculate Benefits | As a customer I need to be able to view how the application(s) benefit me while subscibe to them. | Large | 3 | 3 | Dustin | 24
Note on E3: stakeholdermap.com: Whatever method you are using for estimation. It could be story points, Fibonacci scale or T-shirt sizes - small, medium, large.
Note on F3: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on G3: stakeholdermap.com: To change the Priority menu click on the DROPDOWN MENUS worksheet.
Note on H3: stakeholdermap.com: An optional field for the person responsible for the completion of the User Story.
Note on I3: stakeholdermap.com: This is an optional field for estimated effort in hours or days.

## PROJECT DETAILS
PROJECT NUMBER | 0
PROJECT NAME | DSEED Management
PROJECT MANAGER | Dustin Trinh
DATE | January 6st, 2023
VERSION | 1

## DROPDOWN MENUS
PRIORITY | SPRINT
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
6
7
8
9
10
TO EDIT THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Source to match the values you want to appear in the menu.
TO DELETE THE DROPDOWN MENUS
Click on the Data tab. Under Data Tools, select Data Validation. Under Settings change the Allow to Any value.

## RESOURCES
Useful resources
Burndown Chart Template
Daily Scrum Meeting Template
Project Management Templates
The Top 50 Business Risks (and how to manage them)!
Issue Log Template [free download]
End Project Report Template
Risk Register Template
Stakeholder Management Templates
Work Breakdown Structure (WBS) template in Excel